## Slide 1: ADJUSTED TIMELINE (ADJUSTED)
2023 |  |  |  |  |  |  |  |  |  |  |  | 2024 |  |  |  |  |  |  |  |  |  |  |  | 2025 |  |  |  |  |  |  |  |  |  |  | 
J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D
Stage 2 - 67% Support
Stage 3 - Application
Stage 4 - CoT Approval
Stage 5 - Construction Preparation
Stage 1 - Preparation
Stage 2 – 67% Support
Stage 3 –Application
Stage 4 – CoT Approval
Stage 5 – Construction Preparation
Stage 6 – Construction
Stage 7 - Operational
Evaluate Service Providers
Train Street Captains
Public Meeting
Gain public consent
Traffic Impact Study
Prepare & Submit Application
Follow-up with CoT
Public Objections
Issue Tenders
Wayleaves
Booms
Guardhouses
Signs
Road Markings
Ensure Operational Readiness & Handover
3 months
3 months
2 months
9 months
3 months
9 months
1 month
Stage 1 - Preparation
Present Date
2025 - Stage 6 – Construction